## Release Plan
Release Planning
|  | ID | Story | Estimation | Priority | MVP
|  | 7.2.1 | As an End User I want to be able to ask my questions in plain text | 8 | 1 | 1
| Release Goals: | 7.2.2 | As an End User I want to be able to use English language | 1 | 2 | 1
1 | First release after GUI is functional and can provide basic information | 7.1.1 | As an End User I want to be able to access the chat bot from an easy-to-use GUI | 8 | 3 | 1
2 | Final release when all the remaing stories are done | 7.1.2 | As an End User I want to be able to access the system without an account | 4 | 4 | 1
|  | 7.1.3 | As an End User I want to be provided with an easy to understand message when an error occurs | 2 | 5 | 1
|  | 7.4.12 | As a system Administrator I want the system to provide a nice error to the user when they ask questions outside of the relevant topics | 4 | 6 | 1
|  | 7.3.1 | As an End User I want the system to generate contextually appropriate responses based on my query | 8 | 7 | 1
| First Release (MVP 1) October 17th | 7.2.3 | As a system maintainer I want the system to accurately extract intents with at least 80% accuracy | 8 | 8 | 1
1 | Stories: As marked in MVP column = 1 | 7.3.2 | As an End User I want the system to provide grammatically correct responses | 8 | 9 | 1
2 | Estimation / Velocity = 35 points per sprint (Excluding Sprint 1) | 7.3.3 | As an End User I want the system to support a conversation with me for at least 3 turns while maintaining context | 4 | 10 | 1
|  | 7.6.2 | As a system administrator I want the initial release of ChatCat to be able to support queries from a single user at a time | 4 | 11 | 1
|  | 7.4.11 | As an End User I want the system to ask me a follow up question if my initial question was not specific enough as well as the ability to cancel a request | 8 | 12 | 1
| Second Release (MVP 2) November 28th | 7.4.1 | As an End User I want the system to be able to provide basic information about the BS Software Engineering program at the UofA | 2 | 13 | 1
1 | Stories: As marked in MVP column = 2 | 7.4.2 | As an End User I want the system to be able to provide basic information about the MS Software Engineering program at the UofA | 2 | 14 | 2
2 | Estimation / Velocity = 16 points per sprint | 7.4.3 | As an End User I want the system to be able to provide basic information about the PhD Software Engineering program at the UofA | 2 | 15 | 2
|  | 7.6.3 | As a system maintainer I want the system to provide responses to a user's query or request with at least 80% accuracy | 8 | 16 | 2
|  | 7.4.4 | As an End User I want the system to provide me with contact and scheduling information for the BS SFWE academic advisors | 2 | 17 | 2
| Releases after: | 7.4.5 | As an End User I want the system to provide me with contact and scheduling information for the MS and PhD SFWE academic advisors | 2 | 18 | 2
| Sprint 3, 6 | 7.4.6 | As an End User I want the system to provide information to assist with the degree application and admission process when asked | 4 | 19 | 2
|  | 7.1.4 | As a system maintainer I want to be able to swap components easily without impacting the system | 1 | 20 | 2
|  | 7.4.7 | As an End User I want the system to tell me about career opportunities in the fields of Software Engineering when asked | 4 | 21 | 2
|  | 7.4.8 | As an End User I want the system to provide information about research opportunities when available and asked | 4 | 22 | 2
|  | 7.4.9 | As an End User I want the system to provide direct links to official resources rather than referencing their name | 2 | 23 | 2
|  | 7.4.10 | As an End User I want the system to remember my session if I temporarily lose connection to the system | 8 | 24 | 2
|  | 7.5.1 | As a system administrator I do not what the system to store any personally identifiable information beyond the active session with the user | 1 | 25 | 2
|  | 7.6.1 | As a system administrator I want the system to generate responses within 5 seconds of a user query/request | 8 | 26 | 2
|  | Total |  | 117

## Stories
ID | Story | Estimation | Priority | MVP | Calculations
7.2.1 | As an End User I want to be able to ask my questions in plain text | 8 | 1 | 1 |  | Points | #Sprints | Velocity
7.2.2 | As an End User I want to be able to use English language | 1 | 2 | 1 | MVP1 | 69 | 2 | 35
7.1.1 | As an End User I want to be able to access the chat bot from an easy-to-use GUI | 8 | 3 | 1 | MVP2 | 48 | 3 | 16
7.1.2 | As an End User I want to be able to access the system without an account | 4 | 4 | 1
7.1.3 | As an End User I want to be provided with an easy to understand message when an error occurs | 2 | 5 | 1
7.4.12 | As a system Administrator I want the system to provide a nice error to the user when they ask questions outside of the relevant topics | 4 | 6 | 1
7.3.1 | As an End User I want the system to generate contextually appropriate responses based on my query | 8 | 7 | 1
7.2.3 | As a system maintainer I want the system to accurately extract intents with at least 80% accuracy | 8 | 8 | 1
7.3.2 | As an End User I want the system to provide grammatically correct responses | 8 | 9 | 1
7.3.3 | As an End User I want the system to support a conversation with me for at least 3 turns while maintaining context | 4 | 10 | 1
7.6.2 | As a system administrator I want the initial release of ChatCat to be able to support queries from a single user at a time | 4 | 11 | 1
7.4.11 | As an End User I want the system to ask me a follow up question if my initial question was not specific enough as well as the ability to cancel a request | 8 | 12 | 1
7.4.1 | As an End User I want the system to be able to provide basic information about the BS Software Engineering program at the UofA | 2 | 13 | 1
7.4.2 | As an End User I want the system to be able to provide basic information about the MS Software Engineering program at the UofA | 2 | 14 | 2
7.4.3 | As an End User I want the system to be able to provide basic information about the PhD Software Engineering program at the UofA | 2 | 15 | 2
7.6.3 | As a system maintainer I want the system to provide responses to a user's query or request with at least 80% accuracy | 8 | 16 | 2
7.4.4 | As an End User I want the system to provide me with contact and scheduling information for the BS SFWE academic advisors | 2 | 17 | 2
7.4.5 | As an End User I want the system to provide me with contact and scheduling information for the MS and PhD SFWE academic advisors | 2 | 18 | 2
7.4.6 | As an End User I want the system to provide information to assist with the degree application and admission process when asked | 4 | 19 | 2
7.1.4 | As a system maintainer I want to be able to swap components easily without impacting the system | 1 | 20 | 2
7.4.7 | As an End User I want the system to tell me about career opportunities in the fields of Software Engineering when asked | 4 | 21 | 2
7.4.8 | As an End User I want the system to provide information about research opportunities when available and asked | 4 | 22 | 2
7.4.9 | As an End User I want the system to provide direct links to official resources rather than referencing their name | 2 | 23 | 2
7.4.10 | As an End User I want the system to remember my session if I temporarily lose connection to the system | 8 | 24 | 2
7.5.1 | As a system administrator I do not what the system to store any personally identifiable information beyond the active session with the user | 1 | 25 | 2
7.6.1 | As a system administrator I want the system to generate responses within 5 seconds of a user query/request | 8 | 26 | 2