## Risk Register
SIFWE 503 - Agile Wildcats: Ariel Austin, Justin Larimore, Karri Fox, Richard Gringas, Robert Dillon
Project Objective
Create an intelligent conversational agent that provides students, prospective students, and other stakeholders with quick, accurate, and accessible information about the Software Engineering Bachelor's, Master's, and Doctoral programs offered at the University of Arizona's Software Engineering department.
Risk Register
Risk # | Risk Summary | Mitigation Plan | Likelihood (1-5) | Impact (1-5) | Risk Factor (L x I)
1 | If a new requirement is added mid-development, then the completion of the project will be delayed. | Ask the professor clarifying questions at the beginning of the project to ensure requirements are understood and clearly defined | 5 | 4 | 20 |  |  | See below for Risk Severity Matrix
2 | If a teammate drops from the course or is otherwise unavailable, then our velocity will drop. | Support each other and shift responsibilities when necessary to cover for the absence of a team member. | 1 | 3 | 3
3 | If a technology we are using does not work for our application, then we will have to re-write/edit our code base and plan | Continue to investigate unknowns early so if anything needs to change direction we can do it early | 2 | 4 | 8
4 | If our team is unfamiliar with the technology/code base we are developing, the velocity will be low. | Lean on subject matter experts with experience in the technology and provide training to the inexperienced team members. | 4 | 3 | 12
5 | If there is a conflict within our team, our performance may be negatively impacted | Establish a team contract that addresses conflict resolution. Bring the issue to the professor if it is not resolved within the team. | 1 | 4 | 4
6 | There may not be enough time to complete the entire project within the semester. | No mitigation - plan the project to the fullest capability of the team and report progress on a bi-weekly basis | 3 | 2 | 6
7 | If necessary development tools are unavailable to some of the team members, they will be limitied in how they can contribute to the project. | Research a toolbase that is free and accessible to the entire team, regardless of operating system. | 1 | 5 | 5
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
[8 empty] | Opportunity Matrix |  |  |  |  | Risk Matrix
[6 empty] | Likelihood | 5. Almost Certain |  |  |  | 2 |  |  |  |  | 1
[7 empty] | 4. Likely |  | 4 | 1 |  |  |  |  | 4
[7 empty] | 3. Moderate | 3 | [5 empty] | 6
[7 empty] | 2. Unlikely | [8 empty] | 3
[7 empty] | 1. Rare | [7 empty] | 2 | 5 | 7
[8 empty] | 5. Extreme | 4. Very High | 3. Medium | 2. Low | 1. Negligible | 1. Negligible | 2. Low | 3. Medium | 4. Very High | 5. Extreme
Impact
Opportunity Register
Opportunity # | Opportunity Summary | Realization Plan | Likelihood (1-5) | Impact (1-5) | Opportunity Factor (L x I)
1 | If we find existing code that can be re-used to meet some requirements, then schedule may be reduced. | Research existing projects similar to ours and re-utilize code that makes sense where possible. | 4 | 3 | 12
2 | If we can leverage AI code generation, then we can automate the creation of our unit tests | Start using coding focused "AI"s (Github Copilot, Qwen, etc) to ingest our code and generate test cases | 5 | 2 | 10
3 | If we can utilize team members with higher degrees of domain knowledge and experience, then our team productivity and effectiveness can be increased. | Have experienced team member provide video demonstrations that explain how the code works and gives the rest of the team a tutorial on how to contribute to it. | 3 | 5 | 15
4 | If we can establish a high-performing team, we can have a higher velocity | Establish a regular sprint ceremony schedule that keeps the team synchronized and lean on team member's strengths when assigning stories. | 4 | 4 | 16
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0